EUSE Scholarship 2008 - 2009

Implementation Timetable

| Date | Action | Responsibility |
| --- | --- | --- |
| 12 May 2008 | - Send Draft Application Information and Draft Application Form to EUSE Board Members for review and test. | EUSE Secretariat |
| 16 May 2008 | - National Associations return test Application Forms and comments and also confirm participation. | National Associations |
| Week commencing 26 May 2008 | - Marketing the EUSE Exchange Scholarship Programme to National Association members via email and mailshots. - Information also uploaded onto EUSE website. | EUSE Secretariat |
| Week commencing 26 May 2008 | - National Associations circulate information to members. | National Associations |
| 25 July 2008 | - Closing date for applications. Application Forms must be returned to EUSE Secretariat. - Closing date for Applications must be received by 25 July 2008 – Applications received after this date will not be accepted. - Applications must be sent by email and post. Applications will not be accepted by email or fax. | Applicants |
| 28 July – 31 August 2008 | - If EUSE receives more than 5 applications from each state they will forward the applications to National Associations for first round selection using a selection criteria which will be forwarded. - National Associations must insure that applicants are a member. - 5 Applications should be shortlisted and forwarded to the EUSE Secretariat. - EUSE will contact applicants who have been unsuccessful. | National Associations |
| 20 August – 14 September 2008 | - EUSE Selection. EUSE will select 5 Applications to participate from the total applications received from National Associations. (5 Reserve participants will also be selected.) - As there are only 5 Scholarships there will be only one participant selected from each member state. If, however, there are less than 5 member states participating, there may be two participants selected from a member state. - EUSE will contact and inform the successful applicants and also the unsuccessful applicants. - NB Selection Panel decision is final. - 22 September 2008 – All applicants informed of decision. | EUSE Se lection Panel |
| 1 October 2008– 31 March 2009 | - Exchange Study Visits take place. | Participants |
| 30 April 2008 | - Participant’s Final report (3000 words) forwarded to EUSE. On receiving Final Report and original invoices/receipts, reimbursement of expenses will be paid. | Participants |
| June 2009 | - Dissemination of Report, National Association Information, EUSE Website etc. - Evaluation of EUSE Scholarship Exchange Programme. | EUSE Secretariat |